## Sheet1
Tasks\Month |  | October |  |  | November
|  | 2nd Week | 3rd Week | 4th Week | 1st Week | 2nd Week | 3rd Week | 4th Week
MPI SHARCNET Tasks | Optimal no of Processors |  | Y
Map Reduce | Optimal block size | Y
| Optimal input-split size |  | Y
| Optimal Compression format |  |  | Y
Compile Results |  |  |  |  | Y
Report Writing |  |  |  |  | Y